## Instructions
How do we apply the Plan of Action and Milestones?
1. Once improvement opportunities have been identified, identify a stakeholder who will be responsible for updating the POA&M.
2. Assign each improvement opportunity a stakeholder who is accountable for the task’s completion.
3. For each task, work with stakeholders to determine when task activities should begin, and end, based on policy, resourcing, and other factors.
4. Create a timeline that maps initiation and completion of each task.
5. Monitor and frequently update the POA&M to reflect the status of tasks.
6. Develop cadence for meeting with POA&M task stakeholders to identify barriers to progress and completion and determine methods of mitigation or resolution.

## POA&M Template
POA&M
Task Name | Duration | Start | Finish | Predecessor

## POA&M Example
POA&M
Task Name | Duration | Start | Finish | Predecessor
Establish Baseline | 1 week |  |  | N/A
Perform initial 1.5-mile timed run
Identify indoor running solutions and funding sources
Develop initial structured running plan with knowledgeable friend
Complete initial timed 1.5-mile run, recording baseline time
Initial Progress Assessment Weeks | 3 weeks |  |  | Establish Baseline
Schedule 3–4 runs per week
Track progress weekly
Work on running form
Achieve consistent routine of 3–4 runs weekly
Mid-Program Review | 12 weeks |  |  | Initial Progress Assessment
Evaluate progress weekly and document improvements
Identify and document training obstacles
Modify training regimen based on performance data
Improve initial 1.5-mile time by at least 30 seconds from baseline
Final Adjustment Period | 2 weeks |  |  | Mid-Program Review
Conduct final training plan refinement
Address any remaining obstacles and finalize preparations
Achieve a 1.5-mile run within 15 seconds of the target goal (<14:00)
Final Performance Check | 1 week |  |  | Final Adjustment Period
Perform final timed 1.5‐mile run
Confirm readiness status for PFA
Complete the final timed run at or under 13:45